## Project Planner
Research Plan
[8 empty] | Plan Duration |  |  | % Complete |  |  | % Complete
|  |  |  | Period Highlight: |  | 4 |  | Actual Start |  |  | Actual (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | MONTHS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Thesis Writeup | 1 | 12 | 1 | 12 | 30%
Lit. Review | 1 | 2 | 1 | 2 | 100%
Hardware Setup | 2 | 1 | 2 | 1 | 100%
Firmware Dev | 2 | 2 | 2 | 2 | 100%
Proposal Writeup | 4 | 1 | 4 | 1 | 100%
Calibration | 5 | 1 | 5 | 1 | 0%
Preprocess Data | 5 | 1 | 5 | 1 | 0%
ML Training | 5 | 3 | 5 | 3 | 0%
ML Evaluation | 7 | 1 | 6 | 1 | 0%
Lab Testing | 8 | 1 | 7 | 1 | 0%
User Testing | 8 | 2 | 7 | 2 | 0%
Candidature Defense | 10 | 1 | 10 | 1 | 0%
Thesis Submission | 12 | 1 | 11 | 1 | 0%